## Grant Category Summary
Central Avenue Bicycle and Pedestrian Conversion (STP)
Engineering | 81681.39 | 81700
Equipment Purchase | 0 | 0
Right-of-Way | 0 | 0
Other | 0 | 0
Utility Adjustment/Relocation | 0 | 0
Program Implementation/Construction | 687160.9 | 687200
Contingency | 129653 | 129700
Total Estimated Project Cost | 898495.29 | 898600 | (Does not include the 110k additional bridge improvements)
Federal Amount |  | 700000
Match Amount |  | 198600
Year Requested (2023 or 2024) |  | 2023

## CentralAve_Viaduct
For | KC Levee Trails | 0 | 0 | 0 | Job No. | 76789 | 0 | 0 | Sheet No. | 1 | 0
Made by | KDW | 0 | 0 | 0 | Checked by | 0 | 0 | 0 | Backchecked by | 0 | 0
Date | 2020-03-17 | 0 | 0 | 0 | Date | 0 | 0 | 0 | Date | 0 | 0
Preliminary Estimate - Trailhead and Trail Betterments
ITEM NO. | REFERENCE | ITEM DESCRIPTION | [6 empty] | QTY | UNIT | UNIT COST | TOTAL
1 | General | Demolition | [6 empty] | 1 | LS | 10000 | 10000 | 0
2 | General | Earthwork | [7 empty] | LS | 10000 |  | 0
3 | Utility | Water Service | [7 empty] | LS | 5000 |  | 0
4 | Utility | Electrical Service | [6 empty] | 1 | LS | 5000 | 5000 | 0
5 | Signal | H.A.W.K. Signal | [7 empty] | EA | 35000 |  | Include wiring, conduit, etc.
6 | Paving | Aggregate Paving (6 in.) | [7 empty] | SY | 50 |  | 0
7 | Paving | Asphalt Pavement (6 in.) | [7 empty] | Ton | 90 |  | Ton (140 pounds per cubic foot)
8 | Paving | Concrete Pavement (6 in. Non-Reinf) | [7 empty] | SY | 70 |  | 0
9 | Paving | Concrete Sidewalk Pavement w/ Glow Aggregate (4 in. Non-Reinf) | [7 empty] | SY | 84 |  | 0
10 | Paving | Concrete Sidewalk Pavement (4 in. Non-Reinf) | [7 empty] | SY | 60 |  | 0
11 | Paving | Concrete Curb Ramp | [7 empty] | EA | 2500 |  | 0
12 | Paving | Truncated Domes | [7 empty] | SF | 55 |  | 0
13 | Paving | Concrete Curb and Gutter | [7 empty] | LF | 35 |  | 0
14 | Paving | Striping (6 in. White) | [6 empty] | 2256 | LF | 4 | 9024 | 0
15 | Paving | Striping (24 in. White) | [7 empty] | LF | 22 |  | 0
16 | Paving | Striping (Bike Lane Symbol) | [6 empty] | 4 | EA | 30 | 120
17 | Paving | Striping (Pedestrian Lane Symbol) | [6 empty] | 2 | EA | 30 | 60
18 | Paving | Brick Pavers | [7 empty] | SF | 20 |  | 0
19 | Paving | Crushed Stone Surfacing | [7 empty] | SF | 4 |  | 0
20 | Paving | Boardwalk | [6 empty] | 8297.85 | SF | 15 | 124468 | 4"x8"x20' Timber
21 | Wall | Limestone Block Retaining Wall | [7 empty] | LF | 205 |  | Assumes 4' high wall w/ 6" gravel base (2 courses of limestone block, block dim. = 2'x2'x'6')
22 | Wall | MSE Retaining Wall | [7 empty] | SFF | 60 |  | SFF (Square foot of face), Assumed avg of 8' tall
23 | Stairs | Concrete Stairs | [7 empty] | SF | 12 |  | 0
24 | Tunnel | Pedestrian Tunnel | [7 empty] | EA | 584000 |  | $120/SF for concrete, $100k lighting, $200k Earthwork, no walls or extras.
25 | Landscape | Decorative Gravel | [7 empty] | SF | 5 |  | 0
26 | Landscape | Top Soil amendment (6" depth) | [7 empty] | CY | 10 |  | 0
27 | Landscape | Overstory Trees | [7 empty] | EA | 400 |  | 0
28 | Landscape | Shrub (#1) | [7 empty] | EA | 50
29 | Landscape | Mulch | [7 empty] | CY | 100
30 | Landscape | Sod | [7 empty] | SY | 4 |  | 0
31 | Amenities | Decorative Fence / Screen | [7 empty] | LF | 60 |  | 0
32 | Amenities | Shelter | [7 empty] | EA | 20000 |  | 0
33 | Amenities | Picnic Table | [7 empty] | EA | 3000 |  | 0
34 | Amenities | Trash Receptacle | [7 empty] | EA | 1500 |  | 0
35 | Amenities | Bike Rack | [7 empty] | EA | 1500 |  | 0
36 | Amenities | Bicycle Repair Station | [7 empty] | EA | 1500 |  | 0
37 | Amenities | Limestone Block Bench / Barrier | [6 empty] | 6 | EA | 1400 | 8400 | Needed for East side of bridge
38 | Amenities | 10' Swing Gate | [6 empty] | 1 | EA | 5000 | 5000 | Needed for East side of bridge
39 | Amenities | Water Fountain (Water Bottle Filler, Dog Bowl) | [7 empty] | EA | 6000 |  | 0
40 | Amenities | Concrete Parking Block | [7 empty] | EA | 100 |  | 0
41 | Amenities | Railing | [6 empty] | 1504 | LF | 100 | 150400 | 0
42 | Art | Kinetic Art Wall | [7 empty] | EA | 25000 |  | 0
43 | Art | Mural | [7 empty] | EA | 15000 |  | 0
44 | Signage | Post Marker v1 Trail Sign (A) | [7 empty] | EA | 1700 |  | See page 7 - MARC Wayfindging PDF
45 | Signage | Ground Marker Trail Sign (B) | [7 empty] | EA | 920 |  | 0
46 | Signage | Information v1 Trail Sign (C1) | [7 empty] | EA | 2000 |  | 0
47 | Signage | Information v2 Trail Sign (C2) | [7 empty] | EA | 3300 |  | 0
48 | Signage | Welcome Trail Sign (D) | [7 empty] | EA | 4700
49 | Signage | Information v2 Trail Sign (E) | [6 empty] | 1 | EA | 4200 | 4200 | Needed for East side of bridge
50 | Signage | Post Marker v3 Trail Sign (F) | [7 empty] | EA | 2200 |  | 0
51 | Signage | Arrival Trail Sign (G) | [7 empty] | EA | 3500 |  | 0
52 | Signage | Interpretive Trail Sign (H) | [7 empty] | EA | 3500 |  | Use this for all overlook signs
53 | Signage | Trail Parking / Ped. Crossing Sign | [7 empty] | EA | 500
54 | Lighting | Central Ave. Bridge Lighting | [6 empty] | 2.5 | LS | 20000 | 50000
55 | Lighting | Pedestrian Lighitng | [7 empty] | EA | 4000
56 | Lighting | Column Uplighting | [7 empty] | EA | 3000 |  | 2 uplights per column
57 | 0 | 0 | [7 empty] | 0 | 0
58 | 0 | 0 | [7 empty] | 0 | 0 |  | 0
[11 empty] | Subtotal | 366672
[11 empty] | Mobilization 6% | 22000.32
[11 empty] | Contingency 20% | 73334.4
[11 empty] | Soft Costs/Design 10% | 46200.672
[11 empty] | GRAND TOTAL | 508207.392
Disclaimer:
The costs shown in this estimate represent an estimate of probable costs prepared in good faith and with reasonable care. HNTB has no control over the costs of construction labor, materials, or equipment, nor over competitive bidding or negotiating methods and does not make any commitment or assume any duty to assure that bids or negotiated prices will not vary from this estimate.

## ARM_Central_Trailhead
For | KC Levee Trails | 0 | 0 | 0 | Job No. | 76789 | 0 | 0 | Sheet No. | 1 | 0
Made by | KDW | 0 | 0 | 0 | Checked by | 0 | 0 | 0 | Backchecked by | 0 | 0
Date | 2020-03-17 | 0 | 0 | 0 | Date | 0 | 0 | 0 | Date | 0 | 0
Preliminary Estimate - Trailhead and Trail Betterments
ITEM NO. | REFERENCE | ITEM DESCRIPTION | [6 empty] | QTY | UNIT | UNIT COST | TOTAL
1 | General | Demolition | [6 empty] | 1 | LS | 10000 | 10000 | 0
2 | General | Earthwork | [6 empty] | 4 | LS | 10000 | 40000 | JDW - increase to $30k-$40k
3 | Utility | Water Service | [7 empty] | LS | 5000 |  | 0
4 | Utility | Electrical Service | [6 empty] | 1 | LS | 5000 | 5000 | 0
5 | Signal | H.A.W.K. Signal | [7 empty] | EA | 35000 |  | Include wiring, conduit, etc.
6 | Paving | Aggregate Paving (6 in.) | [7 empty] | SY | 50 |  | 0
7 | Paving | Asphalt Pavement (6 in.) | [7 empty] | Ton | 90 |  | Ton (140 pounds per cubic foot)
8 | Paving | Concrete Pavement (6 in. Non-Reinf) | [6 empty] | 913.7778 | SY | 70 | 63964 | 0
9 | Paving | Concrete Sidewalk Pavement w/ Glow Aggregate (4 in. Non-Reinf) | [7 empty] | SY | 84 |  | 0
10 | Paving | Concrete Sidewalk Pavement (4 in. Non-Reinf) | [7 empty] | SY | 60 |  | 0
11 | Paving | Concrete Curb Ramp | [7 empty] | EA | 2500 |  | 0
12 | Paving | Truncated Domes | [7 empty] | SF | 55 |  | 0
13 | Paving | Concrete Curb and Gutter | [7 empty] | LF | 35 |  | 0
14 | Paving | Striping (6 in. White) | [6 empty] | 887 | LF | 4 | 3548 | 0
15 | Paving | Striping (24 in. White) | [7 empty] | LF | 22 |  | 0
16 | Paving | Striping (Bike Lane Symbol) | [6 empty] | 2 | EA | 30 | 60
17 | Paving | Striping (Pedestrian Lane Symbol) | [6 empty] | 1 | EA | 30 | 30
18 | Paving | Brick Pavers | [7 empty] | SF | 20 |  | 0
19 | Paving | Crushed Stone Surfacing | [6 empty] | 2862 | SF | 4 | 11448 | 0
20 | Paving | Boardwalk | [7 empty] | SF | 15 |  | 4"x8"x20' Timber
21 | Wall | Limestone Block Retaining Wall | [7 empty] | LF | 205 |  | Assumes 4' high wall w/ 6" gravel base (2 courses of limestone block, block dim. = 2'x2'x'6')
22 | Wall | MSE Retaining Wall | [7 empty] | SFF | 60 |  | SFF (Square foot of face), Assumed avg of 8' tall
23 | Stairs | Concrete Stairs | [7 empty] | SF | 12 |  | 0
24 | Tunnel | Pedestrian Tunnel | [7 empty] | EA | 584000 |  | $120/SF for concrete, $100k lighting, $200k Earthwork, no walls or extras.
25 | Landscape | Decorative Gravel | [6 empty] | 2445 | SF | 5 | 12225 | 0
26 | Landscape | Top Soil amendment (6" depth) | [6 empty] | 225.7593 | CY | 10 | 2258 | 0
27 | Landscape | Overstory Trees | [6 empty] | 4 | EA | 400 | 1600 | 0
28 | Landscape | Shrub (#1) | [6 empty] | 940 | EA | 50 | 47000
29 | Landscape | Mulch | [6 empty] | 33.5 | CY | 100 | 3350
30 | Landscape | Sod | [6 empty] | 952.5556 | SY | 4 | 3810 | 0
31 | Amenities | Decorative Fence / Screen | [7 empty] | LF | 60 |  | 0
32 | Amenities | Shelter | [6 empty] | 1 | EA | 20000 | 20000 | 0
33 | Amenities | Picnic Table | [6 empty] | 2 | EA | 3000 | 6000 | 0
34 | Amenities | Trash Receptacle | [6 empty] | 1 | EA | 1500 | 1500 | 0
35 | Amenities | Bike Rack | [6 empty] | 5 | EA | 1500 | 7500 | 0
36 | Amenities | Bicycle Repair Station | [7 empty] | EA | 1500 |  | 0
37 | Amenities | Limestone Block Bench / Barrier | [6 empty] | 15 | EA | 1400 | 21000 | 0
38 | Amenities | 10' Swing Gate | [6 empty] | 1 | EA | 5000 | 5000 | 0
39 | Amenities | Water Fountain (Water Bottle Filler, Dog Bowl) | [7 empty] | EA | 6000 |  | 0
40 | Amenities | Concrete Parking Block | [7 empty] | EA | 100 |  | 0
41 | Amenities | Railing | [6 empty] | 36 | LF | 100 | 3600 | 0
42 | Art | Kinetic Art Wall | [7 empty] | EA | 25000 |  | 0
43 | Art | Mural | [7 empty] | EA | 15000 |  | 0
44 | Signage | Post Marker v1 Trail Sign (A) | [7 empty] | EA | 1700 |  | See page 7 - MARC Wayfindging PDF
45 | Signage | Ground Marker Trail Sign (B) | [7 empty] | EA | 920 |  | 0
46 | Signage | Information v1 Trail Sign (C1) | [7 empty] | EA | 2000 |  | 0
47 | Signage | Information v2 Trail Sign (C2) | [7 empty] | EA | 3300 |  | 0
48 | Signage | Welcome Trail Sign (D) | [6 empty] | 1 | EA | 4700 | 4700 | Use this for all trailheads with a sign
49 | Signage | Information v2 Trail Sign (E) | [7 empty] | EA | 4200 |  | 0
50 | Signage | Post Marker v3 Trail Sign (F) | [7 empty] | EA | 2200 |  | 0
51 | Signage | Arrival Trail Sign (G) | [7 empty] | EA | 3500 |  | 0
52 | Signage | Interpretive Trail Sign (H) | [7 empty] | EA | 3500 |  | Use this for all overlook signs
53 | Signage | Trail Parking / Ped. Crossing Sign | [7 empty] | EA | 500
54 | Lighting | Central Ave. Bridge Lighting | [7 empty] | LS | 20000
55 | Lighting | Pedestrian Lighitng | [6 empty] | 2 | EA | 4000 | 8000
56 | Lighting | Column Uplighting | [7 empty] | EA | 3000
57 | 0 | 0 | [7 empty] | 0 | 0
58 | 0 | 0 | [7 empty] | 0 | 0 |  | 0
[11 empty] | Subtotal | 281593
[11 empty] | Mobilization 6% | 16895.58
[11 empty] | Contingency 20% | 56318.6
[11 empty] | Soft Costs/Design 10% | 35480.718
[11 empty] | GRAND TOTAL | 390287.898
Disclaimer:
The costs shown in this estimate represent an estimate of probable costs prepared in good faith and with reasonable care. HNTB has no control over the costs of construction labor, materials, or equipment, nor over competitive bidding or negotiating methods and does not make any commitment or assume any duty to assure that bids or negotiated prices will not vary from this estimate.